| MGMT490 | Microsoft Project - Assignment 1, Question 2. |
| --- | --- |

Part 1:  Assign Resources for the Office Remodeling Project

# Resources

The following resources are available to this project.  In Project 2007, Click View  Resource Sheet and enter this resource information. In Project 2010, click View/Resource Vides/Resource Sheet.

| Resource Name | Std Rate | Ovt. Rate |
| --- | --- | --- |
| Sally Dehority | 25.76 | 38.64 |
| Mary Watkins | 43.24 | 64.86 |
| Sam Arnold | 23.00 | 34.50 |
| Mike Murran | 43.24 | 64.86 |
| Sherri Webstein | 80.00 | 120.00 |
| Cody Hyatt | 80.00 | 120.00 |
| Henry Mikev | 43.78 | 65.67 |
| Linda Willard | 80.00 | 120.00 |

ADDITIONAL RESOURCE NOTES:

Modify the Standard Calendar to include the following holidays:  Thanksgiving Day, day after Thanksgiving, Christmas Eve, and Christmas.

Also, Mike Murran is going on vacation for five days starting two weeks before the end of the project. . Use the same approach you used to change work hours on Saturday in Part 1. However, you need to update Mike Murran’s calendar (not the standard project calendar).  If you update the standard calendar, you will put the entire project on vacation for five days.

Add the following Resource Assignments to Assignment#1.  Note that the assignment of multiple resources should not decrease the time for the tasks.  So if prompted, respond accordingly. Also, it’s best to select the resources using the drop down arrow instead of typing names yourself.  If you make a typing mistake, you will create new resources with names of people that don’t exist as far as your project is concerned.

Resource Assignment

| Finalize architectural plans | Sally, Henry |
| --- | --- |
| Submit plans to city | Henry |
| Permits obtained | Henry |
| Flooring selected | Sally |
| Flooring installed | Henry |
| File Cabinets Selected | Mike, Sherri, Henry |
| File Cabinet organizers selected | Henry,Sherri |
| File cabinets installed | Sherri |
| File cabinet organizers installed | Sally, Mike |
| Desks Style determined & selected | Cody |
| Desks installed | Cody |
| Cubicle style selected | Cody |
| Cubicle style purchased | Cody |
| Water cooler Purchased | Sally |
| Water cooler Installed | Sally, Sam |
| B/W Copier Purchased | Sally, Henry, Mary |
| B/W Copier Installed | Sherri |
| Color copier selected | Sally |
| Color copier installed | Henry |
| Refrigerator w/ice maker purchased | Sherri |
| Refrigerator w/ice maker installed | Sherri |
| Telephone system chosen | Henry Mary |
| Telephone system installed | Linda |
| Fax machines purchased | Sherri |
| Fax machines installed | Sherri |
| Painting walls | Henry |
| Inspections | Sherri |

Part 2:  Update the Progress of the Office Remodeling Project

The current status:

- Each of the Architects Plans tasks are 100% complete

- Flooring selection and installation are both 100% complete

- File cabinet selection is all 100% complete

- File cabinet installation is 75% complete

- Desk selection is 100% complete

- Desk installation is 55% complete

- All of the Office Equipment has been chosen and purchased – 100% complete

- Water cooler installation is 30% complete

- B/W copier is 40% complete

- Color copier is 60% complete

- Telephone system installation is 58% complete

- Fax machine installation is 39% complete

- Wall painting is 100% complete

Add a footer with your name on it and MS Project #2

Attach your file to this question in Canvas.