## Slide 1: Chapter 14 Special
Project Management

## Slide 2: Runaway Projects and System Failure
Runaway projects: 30–40 percent IT projects
  Exceed schedule, budget
  Fail to perform as specified
Types of system failure
  Fail to capture essential business requirements
  Fail to provide organizational benefits
  Complicated, poorly organized user interface
  Inaccurate or inconsistent data
Notes: This slide emphasizes the high risk of failure for most IT projects and details the main ways a system can be considered to have “failed.” Some studies have shown that only 29 percent of all technology investments are completed on time, on budget, and with all features and functions specified, and nearly 40 percent suffer some kind of failure mode. Ask students what is meant by “Fail to provide organizational benefits” and provide an example.

## Slide 3: Dimensions of Project Risk
Project size
  Cost
  Time
  Number of organizational units affected
  Organizational complexity
Project structure
  Structured, defined requirements run lower risk
Experience with technology
  Team familiar with hardware and software
Notes: This slide discusses a second major factor in evaluating projects, risk. (Remember that portfolio analysis ranks systems according to two criteria, benefit and risk.) Most managers don’t like to think about risk and most make no attempt to measure it. Most managers are optimists and think about benefits. As we all know from the recent financial meltdown, financial managers did not seriously consider risk, and they might be fired if they did. A great many systems projects fail which could have been avoided had managers a better understanding of project risk.
What is meant by risk? Ask students how the size of a project affects its risk. What does organizational complexity mean in this context? Which of these components are organizational versus technical? Can all of them be countered through better project management?

## Slide 4: Change Management and the Concept of Implementation (1 of 2)
Change management
  Required for successful system building
  New information systems have powerful behavioral and organizational impact
Implementation
  All organizational activities working toward adoption, management, and routinization of an innovation
Change agent
  One role of systems analyst
  Redefines the configurations, interactions, job activities, and power relationships of organizational groups
Notes: This slide emphasizes that introduction or alteration of an information system has a powerful behavioral and organizational impact. Change management is required to counter resistance and opposition. Ask students for examples of behavioral and organizational impacts that a new information system might have. What types of changes should an analyst look for in assessing the impact of a new system?
This slide introduces the concept of implementation and the role of the systems analyst as a change agent, a key role in change management efforts. Ask students what types of activities a change agent would engage in to encourage the adoption of a new information system throughout the enterprise. Why don’t employees and managers simply adopt new systems without question?

## Slide 5: Change Management and the Concept of Implementation (2 of 2)
Role of end users
  With high levels of user involvement
    System more likely to conform to requirements
    Users more likely to accept system
User–designer communication gap
  Users and information systems specialists
Management support and commitment
  Effects positive perception by both users and technical staff
  Ensures sufficient funding and resources
  Helps enforce required organizational changes
Notes: Two important factors in successful implementation are user involvement and management support. This slide discusses the role of users and the effects of the user–designer communications gap. Ask students to provide examples of user concerns and designer concerns regarding an information system. What are the goals of these two groups?
This slide discusses a second major factor in successful implementation—management support. It is particularly important to note that if management gives high priority to a project then the project will more likely be treated the same way by users. In what ways can management show support for a project? Which of these are most likely to influence users and technical staff? Why would managers sometimes not show enthusiastic support for a project? (Sometimes, personal, political, and organizational culture differences reduce support for some projects.)

## Slide 6: Change Management Challenges for Business Process Reengineering, Enterprise Applications, and Mergers and Acquisitions
Very high failure rate among enterprise application and BPR projects (up to 70 percent for BPR)
  Poor implementation and change management practices
    Employee concerns about change
    Resistance by key managers
    Changing job functions, career paths, recruitment practices
Mergers and acquisitions
  Similarly high failure rate of integration projects
  Merging of systems of two companies requires:
    Considerable organizational change, complex systems projects
Notes: This slide emphasizes the high failure rate for large-scale enterprise and business process redesign projects and the importance of implementation and change management. To some extent, the failure rate has declined in recent years as the major vendor firms stabilized their offerings, making the technology less of a risk. In turn, large corporations have developed a deep experience base with large scale systems. Nevertheless, large-scale system implementations almost invariably run over budget, and are behind schedule.
Ask students to recall what implementation means. Ask students why both employees and managers become concerned about changes to functions and career paths.